CVPilot

Your AI Career Co-Pilot

Implementation Roadmap

From Architecture to Production

Version 1.0  ·  June 2025

CONFIDENTIAL — EXECUTION DOCUMENT

| Document Type | Implementation Roadmap & Execution Plan |
| --- | --- |
| Authors | CVPilot Founding CTO |
| Status | Approved for Execution |
| References | CVPilot PRD v1.0 · Architecture Document v1.0 |
| Audience | Solo Founder / Engineering Lead |
| Timeline | 4–6 Months to MVP Launch |

# Part 1 — Project Phase Breakdown

The project is divided into 11 phases, each with clear goals, deliverables, and success criteria. Phases are sequential where dependencies exist, but some parallel work is possible from Phase 3 onwards. As a solo founder, phases are time-boxed to 1–3 weeks each.

## Phase 0 — Project Setup (Week 1)

Goals: Establish every tool, account, and repository needed before writing a line of product code. Zero ambiguity from day one.

Deliverables

- GitHub monorepo created with branch protection on main

- Vercel project connected to GitHub (auto-deploy on push)

- Railway project created with staging + production environments

- Neon PostgreSQL database provisioned (staging branch + production)

- Upstash Redis instance created

- Clerk application created (development + production)

- Stripe account created, test mode configured, webhook endpoint registered

- Cloudflare R2 bucket created (private, CORS configured)

- OpenAI API key provisioned, spend limit set ($50 alert, $100 hard cap)

- Resend account created, domain verified

- Sentry project created (frontend + backend)

- Axiom dataset created

- PostHog project created

- .env.example committed with all required variable names (no values)

- Docker Compose file for local development (Postgres + Redis containers)

- ESLint + Prettier + Husky pre-commit hooks configured

Dependencies: None — this is the starting point

✓ Success Criteria: Any engineer can clone the repo and run the project locally in under 10 minutes using the README instructions.

## Phase 1 — Foundation (Week 1–2)

Goals: Scaffold the frontend and backend with all shared infrastructure in place. No features yet — just a correctly wired, deployable skeleton.

Deliverables

- Next.js 14 app initialised with TypeScript, Tailwind CSS, shadcn/ui

- NestJS app initialised with TypeScript, modular structure, class-validator

- TypeORM configured with PostgreSQL connection

- BullMQ configured with Redis connection

- Global exception filter, validation pipe, and logging interceptor in NestJS

- Health check endpoint (GET /health) returning 200

- Axiom logger integrated in NestJS (structured JSON logs)

- Sentry integrated in both frontend and backend

- CI/CD pipeline running (lint → test → build on every PR)

- Deploy pipeline to Railway staging on merge to main

- Vercel deploy connected and working

- CORS configured (frontend origin only)

- Helmet.js security headers configured

Dependencies: Phase 0 complete

✓ Success Criteria: CI pipeline is green. Both apps deploy successfully to staging. /health returns 200. No secrets in git history.

## Phase 2 — Authentication & Users (Week 2–3)

Goals: Users can register, log in, and have an account record in the database. All subsequent phases depend on this.

Deliverables

- Clerk integrated in Next.js (middleware, ClerkProvider, useUser hook)

- Sign-in and sign-up pages using Clerk components

- Google OAuth enabled in Clerk dashboard

- Clerk webhook handler in NestJS (/webhooks/clerk)

- ClerkGuard implemented and applied to all protected routes

- users table migration executed

- profiles table migration executed

- UserModule: UserService, UserController, UserRepository

- POST /api/users/profile — create/update profile

- GET /api/users/me — return current user + profile

- Student email verification logic (.ac.uk domain check)

- GDPR endpoint skeleton: GET /api/gdpr/export, DELETE /api/gdpr/me

- Frontend: protected route wrapper, redirect to sign-in if unauthenticated

- Unit tests: UserService (mock repository)

Dependencies: Phase 1 complete

✓ Success Criteria: A user can sign up, log in with Google, and their account appears in the database. A user not logged in cannot access any /api/* endpoint.

## Phase 3 — CV Management (Week 3–4)

Goals: Users can upload CVs and have them parsed into plain text ready for AI analysis.

Deliverables

- cvs table migration

- R2 presigned URL generation service

- POST /api/cvs/upload-url — generate presigned upload URL

- POST /api/cvs/confirm — confirm upload, create CV record

- GET /api/cvs — list user's CVs

- DELETE /api/cvs/:id — soft delete CV

- BullMQ 'cv-parsing' queue and worker

- CV parsing worker: fetch from R2, extract text from PDF (pdf-parse), extract text from DOCX (mammoth)

- CV record updated with parsed_content and parse_status

- Frontend: CV upload component (drag-drop + file picker)

- Frontend: upload progress indicator

- Frontend: CV list page with status indicators

- File validation: MIME type check, 5MB size limit, PDF/DOCX only

- Error handling: corrupted file, image-only PDF

- Unit tests: CVService, parsing worker

Dependencies: Phase 2 complete

✓ Success Criteria: A logged-in user can upload a PDF CV and see it appear in their list with status 'parsed'. The parsed_content column in the database contains readable plain text from the CV.

## Phase 4 — AI Analysis Engine (Week 4–5)

Goals: The core product value: AI reads a CV against a job description and returns a score and actionable suggestions.

Deliverables

- analyses table migration

- OpenAI SDK integrated (with provider abstraction interface)

- Anthropic SDK integrated (fallback implementation)

- AIService: analyse(cv, jd) → AnalysisResult

- Prompt templates for CV analysis (versioned, in codebase)

- Zod validation schema for AI response

- Retry logic: 3 attempts, exponential backoff

- Circuit breaker: auto-switch to Claude if OpenAI error rate > 5%

- BullMQ 'cv-analysis' queue and worker

- POST /api/analyses — create analysis job

- GET /api/analyses/:id — get analysis result

- GET /api/analyses — list user's analyses

- SSE endpoint: GET /api/analyses/:id/stream — push completion event

- Redis caching: hash(cv_text + jd_text) → cached result, 24h TTL

- tokens_used tracking per analysis

- Frontend: job description input form

- Frontend: analysis results page (score, suggestions, categories)

- Frontend: loading state with SSE progress updates

- Unit tests: AIService (mocked OpenAI), analysis worker

Dependencies: Phase 3 complete

✓ Success Criteria: A user can paste a job description, click Analyse, and within 30 seconds see a match score (0–100) and at least 5 categorised improvement suggestions.

## Phase 5 — ATS Scoring Engine (Week 5)

Goals: Extend the analysis to include ATS-specific keyword matching and format warnings.

Deliverables

- ats_reports table migration

- ATS scoring logic: keyword extraction from JD, keyword matching in CV

- Format warnings: detect common ATS-unfriendly patterns (tables in CV, headers/footers, images)

- ATS score (0–100) stored in ats_reports

- GET /api/analyses/:id/ats — return ATS report

- ATS results integrated into the analysis results UI

- Missing keywords displayed with priority ranking

- Frontend: ATS score component with breakdown

- Unit tests: ATS scoring service

Dependencies: Phase 4 complete

✓ Success Criteria: Analysis results page shows both a match score and a separate ATS score with a list of missing keywords and format warnings.

## Phase 6 — Cover Letter Generator (Week 6)

Goals: Users can generate a tailored cover letter from their CV and job description, edit it inline, and download it.

Deliverables

- cover_letters table migration

- Cover letter generation prompt template (versioned)

- CoverLetterService: generate(cvText, jdText, userProfile) → string

- BullMQ 'cover-letter' queue and worker

- POST /api/cover-letters — generate cover letter

- GET /api/cover-letters/:id — get cover letter

- PATCH /api/cover-letters/:id — update (user edits)

- GET /api/cover-letters — list user's cover letters

- PDF generation: puppeteer or @react-pdf/renderer for download

- DOCX generation: docx library for download

- Uploads to R2, presigned download URL returned

- Frontend: cover letter generation form

- Frontend: inline text editor (simple textarea or Tiptap)

- Frontend: download buttons (PDF + DOCX)

- Frontend: regenerate button

- Unit tests: CoverLetterService (mocked AI)

Dependencies: Phase 4 complete (Phase 5 optional)

✓ Success Criteria: A user can click Generate Cover Letter, receive a personalised 3-4 paragraph letter within 20 seconds, edit it, and download it as a PDF or DOCX.

## Phase 7 — Billing & Subscriptions (Week 7)

Goals: The product can charge users. Free tier is gated. Paid tier is unlocked via Stripe.

Deliverables

- subscriptions table migration

- payments table migration

- Stripe SDK integrated in NestJS

- Stripe webhook handler (/api/webhooks/stripe) with signature verification

- BillingService: createCheckoutSession(), createPortalSession()

- PlanService: getUserPlan(userId), canPerformAction(userId, action)

- BillingGuard: applied to all gated routes

- Webhook events handled: checkout.session.completed, customer.subscription.updated, customer.subscription.deleted, invoice.payment_failed

- POST /api/billing/checkout — create Stripe Checkout Session

- POST /api/billing/portal — create Stripe Customer Portal Session

- GET /api/billing/subscription — get current subscription status

- Usage quota enforcement: free tier limits (2 analyses/mo, 1 cover letter/mo)

- Usage counter in Redis (reset monthly via cron)

- Frontend: pricing page with plan comparison

- Frontend: upgrade prompt/modal on paywall hit

- Frontend: billing settings page (link to Stripe Portal)

- Frontend: usage counter component in dashboard

- Unit tests: BillingService (mocked Stripe), PlanService

- Integration test: Stripe webhook handler

Dependencies: Phase 2 complete

✓ Success Criteria: A free user hitting the paywall sees an upgrade prompt. After paying via Stripe Checkout, they return to the app with full access unlocked within 5 seconds. Cancellation via Stripe Portal works end-to-end.

## Phase 8 — Dashboard & UX Polish (Week 8)

Goals: Users have a coherent, polished experience from landing page to dashboard. Onboarding flow works end-to-end.

Deliverables

- Dashboard: analysis history list with score, job title, company, date

- Dashboard: cover letter history list

- Dashboard: usage counter for free users

- 3-step onboarding flow: Upload CV → Paste JD → See Score

- Landing page: hero, value proposition, pricing, CTA

- Landing page: SEO meta tags (og:title, og:description, structured data)

- Navigation: sidebar for dashboard, top nav for marketing pages

- Empty states for all lists

- Error states for failed analyses

- Responsive design audit (375px – 1440px)

- Favicon, brand colours, typography consistent throughout

- Loading skeletons for async data

- Toast notifications for async events

- Accessibility: keyboard navigation, ARIA labels, colour contrast

Dependencies: Phases 2–7 complete

✓ Success Criteria: A brand new user can discover CVPilot, sign up, upload a CV, paste a JD, see a score, and reach the upgrade prompt in under 3 minutes. The journey has no dead ends.

## Phase 9 — Security Hardening (Week 9)

Goals: Every security requirement from the Architecture Document is implemented and verified before launch.

Deliverables

- Rate limiting: per-user and per-IP rate limits on all endpoints (Throttler)

- Rate limiting: AI endpoints specifically capped (5 req/10min per user)

- Input sanitisation: class-validator on all DTOs, strip unknown fields

- CORS: production origin only (no wildcard)

- Security headers: CSP, HSTS, X-Frame-Options, X-Content-Type-Options via Helmet

- PostgreSQL RLS policies: users can only access their own rows

- File upload: MIME type verification (magic bytes, not just extension)

- Stripe webhook signature verification

- Clerk webhook signature verification

- Secrets audit: no secrets in logs, no secrets in error responses

- GDPR endpoints fully implemented and tested: data export, data deletion

- Audit logging: all sensitive operations logged to audit_logs table

- Penetration test checklist: OWASP Top 10 manual review

- Dependency audit: npm audit passing at high severity

- Environment variable audit: all envs documented, none missing

Dependencies: Phase 8 complete

✓ Success Criteria: OWASP Top 10 checklist completed with no unmitigated HIGH findings. Rate limiting tested. GDPR export and deletion endpoints return correct data and clean up correctly.

## Phase 10 — Production Launch (Week 10)

Goals: CVPilot is live, monitored, and accepting real users.

Deliverables

- Production environment variables set in Railway + Vercel

- Custom domain configured (cvpilot.com) with Cloudflare DNS

- SSL certificate provisioned (Cloudflare + Vercel automatic)

- Stripe live mode activated, live webhook endpoint registered

- Clerk production instance configured

- Cloudflare R2 production bucket with versioning enabled

- BetterUptime monitoring configured (alerts to SMS + email)

- Sentry release tracking configured

- PostHog production analytics running

- OpenAI production API key with $100/month hard cap

- Privacy Policy and Terms of Service pages live

- Cookie consent banner live

- GDPR Data Processing Agreement links in footer

- Launch announcement prepared (Twitter/X, LinkedIn, university boards)

- Smoke test suite run against production

- Rollback plan documented and tested

Dependencies: Phase 9 complete

✓ Success Criteria: A real user in a browser they have never used can discover CVPilot via Google, create an account, analyse a CV, and pay — with no errors in Sentry.

# Part 2 — Sprint Planning

10 sprints across approximately 10 weeks. Each sprint has a clear theme, specific tasks split by concern, and a Definition of Done that is binary — it either passes or it doesn't.

Sprint discipline for a solo founder: time-box each sprint to 5–7 working days. If a sprint is incomplete, carry over tasks, but never skip the Definition of Done check before moving on.

## Sprint 1 — Foundation & Auth (Week 1–2)

Objective: Project fully set up. Both apps deploy. Users can sign up and log in.

Backend Tasks

- NestJS project init with modules skeleton

- TypeORM + PostgreSQL connection

- BullMQ + Redis connection

- ClerkGuard implementation

- Clerk webhook handler (user upsert)

- UserModule: UserService, UserController

- Health check endpoint

- Helmet, CORS, global pipes

- Axiom logger setup

- Sentry backend integration

Frontend Tasks

- Next.js 14 init with TypeScript + Tailwind + shadcn

- Clerk middleware and ClerkProvider

- Sign-in / sign-up pages

- Protected route wrapper

- Basic layout components (sidebar, nav)

- Sentry frontend integration

Database Tasks

- users migration

- profiles migration

- TypeORM data source config

AI Tasks

- None

Testing Tasks

- UserService unit tests (mock repo)

- ClerkGuard unit test

- Health check e2e test

- CI pipeline green

✓ Definition of Done: CI green. Both apps deployed to staging. User can sign up with email + Google and appear in users table.

## Sprint 2 — CV Upload Pipeline (Week 3)

Objective: Users can upload CVs, stored securely in R2, parsed to text in the background.

Backend Tasks

- R2 presigned URL service (upload + download)

- CVModule: CVController, CVService, CVRepository

- POST /api/cvs/upload-url

- POST /api/cvs/confirm

- GET /api/cvs, DELETE /api/cvs/:id

- BullMQ cv-parsing queue

- PDF parsing worker (pdf-parse)

- DOCX parsing worker (mammoth)

- File validation middleware (MIME, size)

- CV parse status updates

Frontend Tasks

- CV upload component (drag-drop + picker)

- Upload progress bar

- CV list page

- CV status badges (pending / parsed / failed)

Database Tasks

- cvs migration

- cv_versions migration (scaffold only)

AI Tasks

- None

Testing Tasks

- CVService unit tests

- Parsing worker unit tests (mock R2 + mock file content)

- Upload flow e2e test

✓ Definition of Done: User uploads a PDF CV. CV appears in list with status 'parsed'. parsed_content in DB contains readable text.

## Sprint 3 — AI Analysis Core (Week 4)

Objective: CV analysis pipeline working end-to-end with score and suggestions.

Backend Tasks

- AIService interface and OpenAI implementation

- Anthropic fallback implementation

- CV analysis prompt template (v1)

- Zod validation schema for analysis response

- BullMQ cv-analysis queue and worker

- AnalysisModule: controller, service, repository

- POST /api/analyses, GET /api/analyses/:id, GET /api/analyses

- SSE endpoint /api/analyses/:id/stream

- Redis cache for analysis results

- Circuit breaker (OpenAI → Claude)

- Token usage tracking

Frontend Tasks

- Job description input form

- Analysis submission flow

- Loading state with SSE progress

- Analysis results page (score + suggestions)

- Suggestion category badges

Database Tasks

- analyses migration

AI Tasks

- CV analysis prompt: write v1, test manually with 10 real CVs

- Tune temperature (0.2)

- Validate JSON output format manually before shipping

Testing Tasks

- AIService unit tests (mocked OpenAI)

- Analysis worker unit tests

- Zod schema validation tests

- Cache hit/miss tests

✓ Definition of Done: User pastes JD, submits, sees score 0–100 and ≥5 suggestions within 30 seconds. Results match Zod schema. Cache serves repeat requests.

## Sprint 4 — ATS Scoring + Cover Letters (Week 5)

Objective: ATS report added. Cover letter generation working end-to-end.

Backend Tasks

- ATS scoring service: keyword extraction, matching, format warnings

- ats_reports table population

- GET /api/analyses/:id/ats

- Cover letter prompt template (v1)

- CoverLetterService with OpenAI

- BullMQ cover-letter queue

- POST /api/cover-letters, GET, PATCH, list

- PDF generation (puppeteer or @react-pdf)

- DOCX generation (docx library)

- Cover letter upload to R2 + presigned download URL

Frontend Tasks

- ATS score component with keyword breakdown

- Missing keywords list

- Cover letter generation form

- Inline text editor for cover letter

- PDF + DOCX download buttons

- Regenerate button

Database Tasks

- ats_reports migration

- cover_letters migration

AI Tasks

- Cover letter prompt: write v1, test with 10 real job + CV pairs

- Tune temperature (0.7 for prose)

- Ensure company name and role appear in output

Testing Tasks

- ATS scoring service unit tests

- CoverLetterService unit tests (mocked AI)

- PDF download e2e test

- Cover letter content validation (company name present, correct length)

✓ Definition of Done: ATS report shown with score and missing keywords. Cover letter generated in <20s, contains company name, downloadable as PDF + DOCX.

## Sprint 5 — Billing & Subscriptions (Week 6)

Objective: Free tier gated. Stripe Checkout working. Subscription state drives access.

Backend Tasks

- BillingModule: BillingService, BillingController

- PlanService: getUserPlan, canPerformAction

- BillingGuard: applied to gated routes

- Stripe checkout session creation

- Stripe customer portal session

- Stripe webhook handler (checkout.session.completed, subscription.updated, subscription.deleted, payment_failed)

- subscriptions table upsert logic

- Usage quota enforcement (Redis counters)

- Monthly cron job: reset usage counters

Frontend Tasks

- Pricing page with plan comparison table

- Upgrade modal / paywall overlay

- Billing settings page (link to Stripe Portal)

- Usage counter component (free users)

- Plan badge in navigation

Database Tasks

- subscriptions migration

- payments migration

AI Tasks

- None

Testing Tasks

- BillingService unit tests (mocked Stripe)

- Stripe webhook handler tests with fixture events

- BillingGuard tests (free vs paid)

- PlanService quota enforcement tests

- Full checkout flow e2e test (Stripe test mode)

✓ Definition of Done: Free user hits paywall, upgrades via Stripe Checkout, returns with access unlocked. Cancellation via portal takes effect at period end. Free tier limits enforced.

## Sprint 6 — Dashboard & Onboarding (Week 7)

Objective: Coherent user experience from landing to first value. Dashboard shows history.

Backend Tasks

- DashboardModule: aggregated queries for history

- GET /api/dashboard/summary — counts + recent items

- Notification events wiring (SSE or polling fallback)

- Resend email integration for account notifications

Frontend Tasks

- Dashboard: analysis history list

- Dashboard: cover letter history list

- Dashboard: empty states

- 3-step onboarding flow

- Landing page: hero, features, pricing, CTA

- SEO meta tags (og:, twitter:, structured data)

- Loading skeletons throughout

- Toast notifications

- Error boundary components

- Responsive design pass (375px–1440px)

Database Tasks

- notifications table migration (optional — can use SSE only for MVP)

AI Tasks

- None

Testing Tasks

- Dashboard query performance test (<200ms p95)

- Onboarding flow e2e test

- Landing page SEO audit (Lighthouse)

✓ Definition of Done: New user completes onboarding in <3 minutes. Dashboard shows all past analyses and cover letters. Landing page scores >80 on Lighthouse.

## Sprint 7 — Security Hardening (Week 8)

Objective: Every security control from the Architecture Document implemented and verified.

Backend Tasks

- Throttler rate limiting (global + per-route)

- AI endpoint rate limiting (5 req/10min per user)

- PostgreSQL RLS policies

- Stripe webhook signature verification (verify already done — double-check)

- Clerk webhook signature verification

- File upload MIME type magic bytes check

- Audit logging service + all sensitive operations logged

- Secrets audit — grep codebase for hardcoded values

Frontend Tasks

- CSP header config in next.config.js

- HSTS, X-Frame-Options, X-Content-Type-Options via Next.js headers

Database Tasks

- RLS policy SQL scripts

- audit_logs migration + indexes

AI Tasks

- Prompt injection review: verify XML delimiters in all prompts

- Test with adversarial CV content (prompt injection attempts)

Testing Tasks

- Rate limit test (exceed limit, verify 429)

- RLS test (try to access another user's data — expect 403/empty)

- Stripe webhook replay test (duplicate event — expect idempotent)

- File upload test (MIME mismatch — expect rejection)

- npm audit — 0 HIGH vulnerabilities

- Manual OWASP Top 10 checklist review

✓ Definition of Done: Rate limiting active. RLS policies live. OWASP checklist complete. npm audit clean. Audit log records all sensitive actions.

## Sprint 8 — GDPR & Compliance (Week 8 (parallel with Sprint 7))

Objective: Full GDPR compliance. Legal pages live. Data handling documented.

Backend Tasks

- GET /api/gdpr/export — ZIP of all user data

- DELETE /api/gdpr/me — full erasure workflow

- Erasure: soft-delete users, schedule R2 file deletion, anonymise analyses

- Clerk account deletion trigger on erasure

- Data retention cron: delete CV files inactive >90 days

Frontend Tasks

- Privacy Policy page

- Terms of Service page

- Cookie consent banner (Cookiebot or custom)

- Account deletion flow in settings

Database Tasks

- deleted_at index on all soft-delete tables

AI Tasks

- Confirm: no CV content sent to OpenAI in fine-tuning or training (default API — confirmed)

Testing Tasks

- GDPR export: verify ZIP contains all user data

- GDPR deletion: verify user data removed from DB and R2 files scheduled for deletion

- Cookie banner: verify analytics blocked before consent

✓ Definition of Done: Privacy Policy and ToS live. GDPR export returns correct ZIP. Deletion flow removes all user data within 72 hours.

## Sprint 9 — Pre-Launch Polish & QA (Week 9)

Objective: End-to-end user journey is smooth, fast, and error-free. Monitoring is live.

Backend Tasks

- PostHog analytics events: sign_up, cv_uploaded, analysis_completed, cover_letter_generated, upgrade_clicked, subscription_started

- BetterUptime monitoring configured

- Sentry release tracking

- Performance: DB query analysis (EXPLAIN ANALYZE on dashboard queries)

- Performance: AI queue depth monitoring

Frontend Tasks

- Full user journey QA on Chrome, Firefox, Safari, Mobile

- Fix all Sentry errors from staging

- Lighthouse performance pass (target >85)

- 404 and error page design

- Favicon + PWA manifest

Database Tasks

- Verify all indexes present

- Run VACUUM ANALYZE

- Connection pool sizing verified

AI Tasks

- Quality audit: run 20 real CV + JD pairs through the pipeline, manually review output quality

- Prompt v2 if any systematic issues found

Testing Tasks

- Full e2e test suite run against staging

- Load test: 50 concurrent analysis requests (k6 or Artillery)

- Cross-browser test

- Mobile device test

✓ Definition of Done: All e2e tests passing. No HIGH Sentry errors. Load test passes. Lighthouse >85. 20-CV quality audit passed.

## Sprint 10 — Production Launch (Week 10)

Objective: CVPilot is live in production, monitored, and accepting real users.

Backend Tasks

- Production environment variables set in Railway

- Stripe live mode webhook endpoint

- OpenAI production API key ($100 cap)

- Final production deploy via CI/CD

Frontend Tasks

- Production domain configured (cvpilot.com)

- Cloudflare DNS + SSL

- Vercel production deployment

- Remove any beta/staging banners

Database Tasks

- Production Neon database migrations run

- Backup schedule verified (daily pg_dump)

AI Tasks

- Monitor first 100 real analyses manually via Axiom

- Set up cost alert at $50 OpenAI spend

Testing Tasks

- Smoke test suite against production (10 critical paths)

- Stripe live mode test transaction

- BetterUptime confirms uptime monitoring active

- Sentry confirms production errors routing correctly

✓ Definition of Done: Production URL live. Real user can sign up, analyse, pay. Sentry clean. Uptime monitor green. First real revenue received.

# Part 3 — GitHub Repository Structure

CVPilot uses a monorepo. Frontend and backend live in the same repository, sharing TypeScript types and configuration. This is the correct choice for a solo founder — one PR, one CI run, one deploy.

cvpilot/                          # Monorepo root

├── apps/

│   ├── web/                      # Next.js frontend

│   └── api/                      # NestJS backend

├── packages/

│   ├── types/                    # Shared TypeScript types (DTOs, API contracts)

│   └── config/                   # Shared ESLint, Prettier, TypeScript configs

├── infra/

│   ├── docker-compose.yml        # Local dev: Postgres + Redis

│   └── scripts/                  # DB seed scripts, migration helpers

├── docs/

│   ├── PRD.md                    # Product Requirements Document

│   ├── architecture.md           # Architecture decisions

│   ├── api.md                    # API reference

│   └── runbooks/                 # Incident runbooks

├── .github/

│   ├── workflows/

│   │   ├── ci.yml                # Lint + test on every PR

│   │   ├── deploy-staging.yml    # Deploy to staging on merge to main

│   │   └── deploy-prod.yml       # Deploy to production (manual trigger or tag)

│   └── PULL_REQUEST_TEMPLATE.md

├── .husky/                       # Pre-commit hooks (lint, type-check)

├── .env.example                  # All required env var names (no values)

├── package.json                  # Root workspace (npm workspaces)

├── turbo.json                    # Turborepo build pipeline

└── README.md                     # Setup instructions

## Key Decisions

- Turborepo for build orchestration — parallel builds, caching, dependency graph.

- packages/types contains shared interfaces like AnalysisResult, UserProfile, SubscriptionPlan — one source of truth between frontend and backend.

- infra/ is not production infrastructure (no Terraform at MVP scale) — just local dev utilities and DB scripts.

- docs/ lives in the repo — documentation that drifts from the codebase is useless.

- No separate packages for UI components at MVP — shadcn/ui lives in apps/web. Extract to packages/ui when a second frontend surface exists.

# Part 4 — NestJS Backend Structure

apps/api/src/

├── main.ts                        # Bootstrap: Helmet, CORS, validation pipe, Swagger

├── app.module.ts                  # Root module — imports all feature modules

│

├── modules/

│   ├── auth/

│   │   ├── auth.module.ts

│   │   ├── guards/

│   │   │   ├── clerk.guard.ts     # Validates Clerk JWT on every protected route

│   │   │   └── billing.guard.ts   # Checks plan and quota before gated actions

│   │   ├── decorators/

│   │   │   └── current-user.decorator.ts

│   │   └── webhooks/

│   │       └── clerk.webhook.ts   # POST /webhooks/clerk

│   │

│   ├── users/

│   │   ├── users.module.ts

│   │   ├── users.controller.ts    # GET /me, PATCH /profile

│   │   ├── users.service.ts       # Business logic

│   │   ├── users.repository.ts    # TypeORM queries

│   │   ├── dto/

│   │   │   ├── update-profile.dto.ts

│   │   │   └── user-response.dto.ts

│   │   └── entities/

│   │       ├── user.entity.ts

│   │       └── profile.entity.ts

│   │

│   ├── cvs/

│   │   ├── cvs.module.ts

│   │   ├── cvs.controller.ts      # upload-url, confirm, list, delete

│   │   ├── cvs.service.ts

│   │   ├── cvs.repository.ts

│   │   ├── dto/

│   │   ├── entities/cv.entity.ts

│   │   └── workers/

│   │       └── cv-parsing.worker.ts  # BullMQ worker

│   │

│   ├── analysis/

│   │   ├── analysis.module.ts

│   │   ├── analysis.controller.ts

│   │   ├── analysis.service.ts

│   │   ├── analysis.repository.ts

│   │   ├── dto/

│   │   ├── entities/

│   │   │   ├── analysis.entity.ts

│   │   │   └── ats-report.entity.ts

│   │   ├── workers/

│   │   │   └── cv-analysis.worker.ts

│   │   └── prompts/

│   │       └── cv-analysis.prompt.ts  # Versioned prompt template

│   │

│   ├── cover-letter/

│   │   ├── cover-letter.module.ts

│   │   ├── cover-letter.controller.ts

│   │   ├── cover-letter.service.ts

│   │   ├── cover-letter.repository.ts

│   │   ├── dto/

│   │   ├── entities/cover-letter.entity.ts

│   │   ├── workers/

│   │   │   └── cover-letter.worker.ts

│   │   └── prompts/

│   │       └── cover-letter.prompt.ts

│   │

│   ├── billing/

│   │   ├── billing.module.ts

│   │   ├── billing.controller.ts  # checkout, portal, subscription status

│   │   ├── billing.service.ts

│   │   ├── plan.service.ts        # getUserPlan, canPerformAction

│   │   ├── dto/

│   │   ├── entities/

│   │   │   ├── subscription.entity.ts

│   │   │   └── payment.entity.ts

│   │   └── webhooks/

│   │       └── stripe.webhook.ts  # POST /webhooks/stripe

│   │

│   ├── dashboard/

│   │   ├── dashboard.module.ts

│   │   ├── dashboard.controller.ts  # GET /dashboard/summary

│   │   └── dashboard.service.ts     # Aggregated read queries

│   │

│   ├── notifications/

│   │   ├── notifications.module.ts

│   │   ├── notifications.service.ts  # Email via Resend, SSE events

│   │   └── sse/

│   │       └── sse.controller.ts     # GET /sse/analyses/:id

│   │

│   └── gdpr/

│       ├── gdpr.module.ts

│       ├── gdpr.controller.ts     # GET /gdpr/export, DELETE /gdpr/me

│       └── gdpr.service.ts

│

├── shared/

│   ├── ai/

│   │   ├── ai.service.ts          # Provider abstraction interface

│   │   ├── openai.service.ts      # Primary provider

│   │   ├── anthropic.service.ts   # Fallback provider

│   │   └── ai-cache.service.ts    # Redis caching layer

│   ├── storage/

│   │   └── r2.service.ts          # Cloudflare R2 presigned URLs

│   ├── audit/

│   │   ├── audit.service.ts       # Write-only audit log service

│   │   └── audit.entity.ts

│   └── events/

│       └── event-bus.service.ts   # NestJS EventEmitter wrapper

│

├── config/

│   ├── database.config.ts

│   ├── redis.config.ts

│   ├── clerk.config.ts

│   ├── stripe.config.ts

│   ├── openai.config.ts

│   └── r2.config.ts

│

└── database/

└── migrations/

├── 001_create_users.ts

├── 002_create_profiles.ts

├── 003_create_cvs.ts

├── 004_create_analyses.ts

├── 005_create_ats_reports.ts

├── 006_create_cover_letters.ts

├── 007_create_subscriptions.ts

├── 008_create_payments.ts

└── 009_create_audit_logs.ts

# Part 5 — Next.js Frontend Structure

apps/web/

├── app/                           # Next.js App Router

│   ├── layout.tsx                 # Root layout (ClerkProvider, fonts, analytics)

│   ├── page.tsx                   # Landing page (/)

│   ├── (auth)/                    # Auth route group (no dashboard layout)

│   │   ├── sign-in/page.tsx       # Clerk SignIn component

│   │   └── sign-up/page.tsx       # Clerk SignUp component

│   ├── (dashboard)/               # Protected route group

│   │   ├── layout.tsx             # Dashboard layout (sidebar + auth check)

│   │   ├── dashboard/page.tsx     # Main dashboard (history summary)

│   │   ├── onboarding/page.tsx    # 3-step onboarding flow

│   │   ├── cvs/

│   │   │   ├── page.tsx           # CV list

│   │   │   └── upload/page.tsx    # Upload flow

│   │   ├── analyse/

│   │   │   ├── page.tsx           # Start new analysis (select CV + paste JD)

│   │   │   └── [id]/page.tsx      # Analysis results

│   │   ├── cover-letters/

│   │   │   ├── page.tsx           # Cover letter history

│   │   │   └── [id]/page.tsx      # Cover letter editor + download

│   │   ├── billing/page.tsx       # Subscription status + portal link

│   │   └── settings/page.tsx      # Profile, student verification, account deletion

│   ├── pricing/page.tsx           # Public pricing page

│   ├── privacy/page.tsx           # Privacy Policy

│   ├── terms/page.tsx             # Terms of Service

│   └── api/                       # Next.js API routes (thin proxy to NestJS)

│       └── [...path]/route.ts     # Proxy all /api/* to NestJS backend

│

├── components/

│   ├── ui/                        # shadcn/ui components (auto-generated)

│   ├── layout/

│   │   ├── sidebar.tsx

│   │   ├── top-nav.tsx

│   │   └── footer.tsx

│   ├── cv/

│   │   ├── cv-upload-zone.tsx     # Drag-drop upload

│   │   ├── cv-list.tsx

│   │   └── cv-card.tsx

│   ├── analysis/

│   │   ├── analysis-form.tsx      # JD input form

│   │   ├── score-ring.tsx         # Circular score display

│   │   ├── suggestion-list.tsx

│   │   ├── suggestion-card.tsx

│   │   └── ats-report.tsx

│   ├── cover-letter/

│   │   ├── cover-letter-editor.tsx

│   │   └── download-buttons.tsx

│   ├── billing/

│   │   ├── pricing-card.tsx

│   │   ├── upgrade-modal.tsx

│   │   └── usage-counter.tsx

│   └── shared/

│       ├── loading-skeleton.tsx

│       ├── error-boundary.tsx

│       ├── empty-state.tsx

│       └── page-header.tsx

│

├── hooks/

│   ├── use-cv-upload.ts           # Upload state machine

│   ├── use-analysis-stream.ts     # SSE connection for live updates

│   ├── use-user-plan.ts           # Current plan + quota

│   └── use-toast.ts               # shadcn toast wrapper

│

├── lib/

│   ├── api-client.ts              # Typed fetch wrapper (all API calls here)

│   ├── utils.ts                   # cn(), formatDate(), etc.

│   └── constants.ts               # Plan limits, routes, etc.

│

├── types/

│   └── index.ts                   # Re-exports from packages/types

│

├── middleware.ts                  # Clerk auth middleware (protects dashboard routes)

├── next.config.js                 # Security headers, rewrites

└── tailwind.config.js

# Part 6 — Database Implementation Order

Migrations are code. They are committed to git, version-controlled, and run automatically on deploy. Never modify a migration after it has been run in production — write a new migration instead.

| Order | Table | Rationale | Initial Indexes |
| --- | --- | --- | --- |
| 001 | users | Foundation. All other tables reference this. No foreign keys yet. | clerk_id, email indexes |
| 002 | profiles | user_id FK → users.id. Safe now that users exists. | user_id unique index |
| 003 | subscriptions | user_id FK → users.id. Billing module depends on auth, not CV. | stripe_customer_id unique |
| 004 | payments | user_id FK → users.id. Subscription FK added in migration 003 first. | stripe_payment_id unique |
| 005 | cvs | user_id FK → users.id. Must exist before analyses. | user_id, parse_status |
| 006 | analyses | user_id + cv_id FKs. Both must exist first. | user_id + created_at composite |
| 007 | ats_reports | analysis_id FK → analyses.id. Analyses must exist first. | analysis_id unique |
| 008 | cover_letters | user_id + cv_id + analysis_id (nullable) FKs. | user_id + created_at composite |
| 009 | audit_logs | user_id FK (nullable). No other dependencies — append-only table. | user_id + created_at, entity_type + entity_id |

## Performance Index Strategy

Not all indexes should be created in the initial migration. Some indexes add write overhead and should only be added when query patterns are confirmed by real usage.

| When | Indexes | Reason |
| --- | --- | --- |
| Phase 0 (with table) | All primary keys (UUID), all unique constraints, all FK indexes | Required for correctness and FK enforcement |
| Phase 1 (at launch) | analyses(user_id, created_at DESC), cover_letters(user_id, created_at DESC), audit_logs(user_id, created_at DESC) | Dashboard queries will run immediately on launch |
| Phase 2 (after 1k users) | analyses(status) WHERE status='pending', cvs(parse_status) WHERE parse_status='pending' | Queue monitoring queries. Partial indexes — only created once queue volume justifies them. |
| Phase 3 (after 5k users) | audit_logs(entity_type, entity_id) | Admin tooling. Not needed at MVP scale. |

# Part 7 — API Implementation Order

All API routes are prefixed with /api/v1/. Versioning is path-based. The v1 prefix is added from day one — changing it later is significantly more painful than including it from the start.

## Authentication & Users

| Method | Endpoint | Priority | Auth | Notes |
| --- | --- | --- | --- | --- |
| POST | /webhooks/clerk | 1 — Critical | None | Clerk signature header |
| GET | /api/v1/users/me | 1 — Critical | Auth | Returns user + profile |
| PATCH | /api/v1/users/profile | 2 | Auth | UpdateProfileDto (class-validator) |
| GET | /api/v1/gdpr/export | 8 | Auth | Returns signed ZIP URL |
| DELETE | /api/v1/gdpr/me | 8 | Auth | Initiates full erasure workflow |

## CV Management

| Method | Endpoint | Priority | Auth | Notes |
| --- | --- | --- | --- | --- |
| POST | /api/v1/cvs/upload-url | 3 | Auth + Plan | Returns presigned R2 URL + CV ID |
| POST | /api/v1/cvs/confirm | 3 | Auth | Confirms upload, enqueues parsing |
| GET | /api/v1/cvs | 3 | Auth | List user's CVs (paginated) |
| GET | /api/v1/cvs/:id | 4 | Auth + Owner | Single CV with parse status |
| DELETE | /api/v1/cvs/:id | 5 | Auth + Owner | Soft delete |

## Analysis

| Method | Endpoint | Priority | Auth | Notes |
| --- | --- | --- | --- | --- |
| POST | /api/v1/analyses | 4 — Core | Auth + Plan | CreateAnalysisDto: cv_id, job_description, job_title, company_name |
| GET | /api/v1/analyses | 4 | Auth | List (paginated, sorted by created_at DESC) |
| GET | /api/v1/analyses/:id | 4 | Auth + Owner | Full analysis result + suggestions |
| GET | /api/v1/analyses/:id/ats | 5 | Auth + Owner | ATS report |
| GET | /api/v1/analyses/:id/stream | 4 | Auth + Owner | SSE stream for live status updates |

## Cover Letters

| Method | Endpoint | Priority | Auth | Notes |
| --- | --- | --- | --- | --- |
| POST | /api/v1/cover-letters | 6 | Auth + Plan | CreateCoverLetterDto: cv_id, analysis_id (opt), job_title, company_name |
| GET | /api/v1/cover-letters | 6 | Auth | List user's cover letters |
| GET | /api/v1/cover-letters/:id | 6 | Auth + Owner | Full content + download URL |
| PATCH | /api/v1/cover-letters/:id | 6 | Auth + Owner | Update content (user edits) |
| POST | /api/v1/cover-letters/:id/download | 6 | Auth + Owner | Generate PDF/DOCX, return signed URL |
| DELETE | /api/v1/cover-letters/:id | 7 | Auth + Owner | Soft delete |

## Billing

| Method | Endpoint | Priority | Auth | Notes |
| --- | --- | --- | --- | --- |
| POST | /api/v1/billing/checkout | 7 — Critical | Auth | Creates Stripe Checkout Session, returns URL |
| POST | /api/v1/billing/portal | 7 | Auth | Creates Stripe Customer Portal Session |
| GET | /api/v1/billing/subscription | 7 | Auth | Returns plan, status, period end, usage |
| POST | /webhooks/stripe | 7 — Critical | Stripe sig | Handles all Stripe events |

## Dashboard

| Method | Endpoint | Priority | Auth | Notes |
| --- | --- | --- | --- | --- |
| GET | /api/v1/dashboard/summary | 8 | Auth | Returns counts: analyses, cover letters, usage, recent items |

## Validation Requirements

- All POST/PATCH endpoints use NestJS class-validator DTOs. Unknown fields are stripped (whitelist: true, forbidNonWhitelisted: true in global validation pipe).

- File MIME type validated against magic bytes (not just Content-Type header) in the CV upload confirmation step.

- Job description length: minimum 50 characters, maximum 10,000 characters.

- All IDs validated as UUIDs. A non-UUID in a route parameter returns 400, not 500.

- Ownership verified on every :id route — a user cannot access another user's resource.

# Part 8 — AI Implementation Roadmap

Build the AI layer in this exact order. Each step is testable in isolation before the next is added. Do not attempt to build the full pipeline in one sprint.

| Step | Task | When | Notes |
| --- | --- | --- | --- |
| Step 1 | CV Parsing (no AI) | Week 3 | Use pdf-parse for PDFs, mammoth for DOCX. Extract plain text. No AI involved. Test with 20 real CVs — verify text quality. |
| Step 2 | Single OpenAI call (manual) | Week 4, Day 1 | Write the analysis prompt. Call OpenAI manually (curl or Postman). Review output for 10 different CV + JD combinations. Fix prompt before writing code. |
| Step 3 | Zod schema + validation | Week 4, Day 2 | Define the exact JSON schema you expect. Write Zod validation. Parse manual OpenAI outputs against it. Find edge cases. |
| Step 4 | AIService abstraction | Week 4, Day 2 | Interface: analyse(cv: string, jd: string): Promise<AnalysisResult>. OpenAI implementation. Test with mocked HTTP. |
| Step 5 | Analysis worker | Week 4, Day 3 | BullMQ worker that calls AIService. Retry logic. Status updates. Persist result. Test end-to-end with a real CV. |
| Step 6 | Redis caching | Week 4, Day 4 | Hash the input. Cache the output. Verify cache hit on repeated identical request. Verify cache miss on changed JD. |
| Step 7 | Anthropic fallback | Week 4, Day 5 | Implement ClaudeService with same interface. Circuit breaker: if OpenAI errors >5% in 5 min, route to Claude. Test failover manually. |
| Step 8 | ATS scoring | Week 5, Day 1–2 | Extend analysis prompt OR separate prompt for keyword extraction. Return keyword_hits array. Store in ats_reports. |
| Step 9 | Cover letter generation | Week 5, Day 3–5 | New prompt template. Higher temperature (0.7). Test with 20 pairs. Verify company name and role appear. Verify no placeholder brackets. |
| Step 10 | Quality audit | Week 9 | Run 20 real CV + JD combinations through the full pipeline. Manually review every output. Fix any systematic issues. Update prompt templates if needed. |

## Prompt Template Structure

All prompts follow this structure. Never embed user content in the system prompt.

// analysis.prompt.ts

export const ANALYSIS_SYSTEM_PROMPT = `

You are an expert CV analyst. Analyse the provided CV against the job description.

Respond ONLY with a valid JSON object matching this exact schema:

{

"match_score": number (0-100),

"suggestions": [{

"category": "MISSING_KEYWORD" | "WEAK_LANGUAGE" | "STRUCTURE" | "ATS_WARNING",

"priority": "HIGH" | "MEDIUM" | "LOW",

"text": string (min 20 chars, max 300 chars)

}],

"ats_keywords": [{"keyword": string, "found": boolean}]

}

Rules:

- Base analysis ONLY on content provided. Do not infer unstated experience.

- Return between 5 and 15 suggestions.

- Do not include any text outside the JSON object.

`;

export const buildAnalysisPrompt = (cvText: string, jdText: string) => [

{ role: 'system', content: ANALYSIS_SYSTEM_PROMPT },

{ role: 'user', content:

`<JOB_DESCRIPTION>\n${jdText}\n</JOB_DESCRIPTION>\n\n` +

`<CV_CONTENT>\n${cvText}\n</CV_CONTENT>` }

];

## Cost Control Implementation

- Set max_tokens: 1500 on every analysis call. 800 on cover letter calls.

- Truncate CV text to 4000 tokens before sending (use tiktoken to count).

- Truncate JD text to 2000 tokens before sending.

- Enable OpenAI prompt caching — system prompt cached at 0.5x cost.

- Redis cache key: SHA256(cvText + jdText). TTL: 86400 seconds (24 hours).

- Log tokens_used to database on every call. Alert if a single call exceeds 3000 tokens.

# Part 9 — Security Implementation Checklist

This checklist must be completed and checked off before the production launch. Every item is binary: done or not done.

## Authentication & Authorization

- ClerkGuard applied to ALL routes in the API except /health, /webhooks/clerk, /webhooks/stripe

- BillingGuard applied to all gated routes (analysis creation, cover letter generation, downloads)

- Ownership check on every :id route (user can only access their own resources)

- Clerk production instance uses a separate API key from development

- Clerk webhook secret verified on every inbound webhook

- JWT expiry: 1 hour (Clerk default — verify not overridden)

## Rate Limiting

- Global rate limit: 200 requests per minute per IP (Throttler)

- Analysis endpoint: 5 requests per 10 minutes per user (Redis token bucket)

- Cover letter endpoint: 5 requests per 10 minutes per user

- Upload URL endpoint: 10 requests per hour per user

- Auth endpoints: not rate limited by us (Clerk handles this)

- Rate limit headers returned (X-RateLimit-Remaining, Retry-After)

## Input Validation

- Global ValidationPipe: whitelist: true, forbidNonWhitelisted: true, transform: true

- All DTOs use class-validator decorators — no manual validation

- UUIDs in route params validated with @IsUUID() — non-UUIDs return 400

- Job description: @IsString(), @MinLength(50), @MaxLength(10000)

- File upload: MIME type checked against magic bytes (not just Content-Type)

- File size: enforced at presigned URL generation (R2 will reject oversized uploads)

## File Security

- R2 bucket is private — no public access

- Presigned URLs expire in 15 minutes

- Presigned URLs are user-scoped (object key includes user_id)

- CV files never served directly from the API — always via presigned URL

- File type: only PDF and DOCX accepted

- Maximum file size: 5MB

- Virus scanning: flag for V2 — document current limitation

## Stripe Security

- Stripe webhook signature verified with stripe.webhooks.constructEvent() on every event

- Webhook handler is idempotent — processing the same event twice is safe

- Stripe secret key only in environment variables — never logged, never returned in responses

- Stripe publishable key only used in frontend (safe to expose)

- No custom payment form — Stripe Checkout handles all card data

## Secrets & Configuration

- No secrets in git history (run: git log --all --full-history -- .env)

- All secrets in Railway environment variables (production) and .env.local (development)

- .env.example committed with variable names but no values

- No hardcoded URLs, credentials, or API keys anywhere in the codebase

- npm audit runs in CI — pipeline fails on HIGH vulnerabilities

## HTTP Security Headers

- Content-Security-Policy: configured in next.config.js

- Strict-Transport-Security: max-age=31536000; includeSubDomains

- X-Frame-Options: DENY

- X-Content-Type-Options: nosniff

- Referrer-Policy: strict-origin-when-cross-origin

- Helmet.js configured in NestJS main.ts

## Logging & Monitoring

- Sensitive data never logged: no CV content, no JD text, no email in logs

- Audit log entries created for: cv.uploaded, analysis.created, analysis.completed, cover_letter.generated, subscription.created, subscription.cancelled, gdpr.export, gdpr.deletion

- Sentry configured with PII scrubbing (email, name stripped from error reports)

- Axiom log retention: 30 days

- BetterUptime health check configured for production URL

## GDPR

- Privacy Policy published at /privacy — mentions all data processors (Clerk, OpenAI, Stripe, Cloudflare)

- Terms of Service published at /terms

- Cookie consent banner implemented — analytics blocked before consent

- GET /api/v1/gdpr/export returns ZIP of all user data within 30 minutes

- DELETE /api/v1/gdpr/me completes full erasure within 72 hours (async)

- CV files scheduled for R2 deletion within 72 hours of erasure request

- OpenAI API used without fine-tuning — CV content is not used for training (confirmed in API docs)

- Data retention policy: CV files deleted after 90 days of inactivity (cron job)

# Part 10 — MVP Definition

The MVP is the smallest thing that can charge a real user real money and make them measurably more likely to get an interview. Everything else is a distraction until paying users exist.

## MVP — Ship at Launch

| Feature | Scope | Justification |
| --- | --- | --- |
| CV Upload | PDF and DOCX, up to 5MB, parsed to text | Core — without this, nothing works |
| CV-JD Analysis | Match score 0–100, 5–15 categorised suggestions | Core value proposition |
| ATS Report | Keyword hits, missing keywords, ATS score | Extends analysis — high perceived value |
| Cover Letter Generation | AI-generated 3–4 paragraph letter based on CV + JD | Second core feature — drives upgrades |
| Cover Letter Editor | Inline editing of generated letter | Required for download to be useful |
| PDF + DOCX Download | Both formats for CV feedback report and cover letter | Tangible output — makes value real |
| User Authentication | Email + Google OAuth via Clerk | Required |
| Subscription Billing | Free tier (2 analyses, 1 letter/mo) + Pro (£9.99) + Student (£4.99) | Required to generate revenue |
| Dashboard | Analysis and cover letter history | Required for retention |
| Onboarding Flow | 3-step: Upload → JD → Score | Required for conversion |
| GDPR Compliance | Privacy policy, cookie consent, data export, deletion | Legal requirement (EU users) |

## Post-MVP — After First 200 Paying Users

| Feature | Description | Why Deferred |
| --- | --- | --- |
| AI Chat Interface | Follow-up questions on analysis results | Wait for user demand signal |
| LinkedIn Profile Optimiser | Analyse LinkedIn profile against JD | Separate surface — scope risk at MVP |
| 7-Day Free Trial | Pro trial without credit card | A/B test after baseline conversion rate known |
| Referral Programme | Invite friends, earn credits | Wait for organic sharing data |
| University Partnerships | Direct B2B channel | Requires sales motion — post-revenue |
| MFA | TOTP via Clerk (config flag) | Enable when enterprise users emerge |

## Version 2 — Month 4–6 Post-Launch

| Feature | Description | Notes |
| --- | --- | --- |
| CV Builder / Template Editor | Create CV from scratch with AI assistance | Different product surface — validate demand first |
| Interview Preparation | Practice questions based on JD + CV | Different use case — different session type |
| Browser Extension | Analyse JDs directly from job boards | High engineering effort — validate core first |
| API Access | For university career centres | B2B product motion — needs dedicated effort |

## Version 3 — Year 2

- Mobile native app (iOS + Android)

- Multi-language support (French, Spanish, German)

- Integration with job boards (Indeed, LinkedIn Easy Apply)

- Team and institutional plans

- AI coaching conversation (full LLM chat interface)

# Part 11 — Final CTO Execution Plan

The goal is not to build a perfect product. The goal is to find 200 people who love what you built, charge them for it, and learn from them. Everything else is noise.

## 11.1 Week-by-Week Plan

| Week | Phase | Focus |
| --- | --- | --- |
| Week 1 | Phase 0 + Phase 1 | Every tool set up. Both apps deploy to staging. CI green. README works. Health check returns 200. This week is about removing all friction from the development process. |
| Week 2 | Phase 2 (Auth) | Users can sign up and log in. Clerk webhook creates DB record. Protected routes work. Do NOT skip writing tests this week — auth bugs discovered in week 8 are expensive. |
| Week 3 | Phase 3 (CV Upload) | CV upload, R2 storage, background parsing all working. Test with 20 real CVs including edge cases (image-only PDF, password-protected, huge files). Fix edge cases now. |
| Week 4 | Phase 4 (AI Analysis) | The make-or-break week. Write the prompt manually on Day 1. Test it manually on Day 2. Then write the code. Do not skip manual prompt testing — it saves days of debugging. |
| Week 5 | Phase 5 + 6 (ATS + Cover Letters) | ATS is an extension of analysis — should be fast. Cover letter generation is the second AI pipeline. Reuse the AIService abstraction. The download (PDF/DOCX) is the hardest technical part of this week. |
| Week 6 | Phase 7 (Billing) | Stripe integration. This is the most important week commercially. Test every webhook event. Test failed payments. Test cancellation. Test downgrade at period end. Use Stripe's test event simulator. |
| Week 7 | Phase 8 (Dashboard + UX) | Polish week. Landing page, onboarding, empty states, loading states, error states, responsive design. This is the week that turns a functional product into something users want to pay for. |
| Week 8 | Phase 9 + GDPR (Security) | Security hardening and compliance. Run the full security checklist. No shortcuts. A security incident before launch would be fatal for a consumer product handling CVs. |
| Week 9 | QA + Polish | Full end-to-end QA. Fix every Sentry error from staging. Run the 20-CV AI quality audit. Load test. Cross-browser test. Lighthouse performance pass. |
| Week 10 | Launch | Production deploy. Domain live. First real users. Monitor Sentry obsessively for 48 hours. Fix any P0 bugs immediately. Do not add features this week. |

## 11.2 Biggest Risks

| Risk | Severity | Mitigation |
| --- | --- | --- |
| AI quality disappoints users | Critical | Manual prompt testing with 20 real CVs before shipping. Quality audit in week 9. Have a 'report bad feedback' mechanism at launch. |
| Scope creep kills timeline | High | The MVP feature list is locked. If a new feature idea feels urgent, write it down and add it to the V2 list. Do not build it now. |
| Solo founder burnout | High | Time-box sprints. Ship on time even if not perfect. A shipped imperfect product beats an unshipped perfect one every time. |
| Stripe webhook handler bugs | High | Test every webhook event type in test mode before going live. Idempotency is critical — test duplicate events explicitly. |
| GDPR compliance after launch | Medium | Build GDPR endpoints in Sprint 8, not after launch. EU students are the primary market. A GDPR violation kills the product. |
| OpenAI API cost spike | Medium | Set hard cap at $100/month. Alert at $50. Monitor tokens_used per user weekly. Anomaly detection in Axiom. |

## 11.3 Biggest Technical Challenges

- PDF parsing quality: image-only PDFs (scanned documents) will return empty text. pdf-parse only handles text-layer PDFs. Detect this case early and show a user-friendly error. Virus scanning is out of scope for MVP but document the gap.

- SSE reliability: Server-Sent Events require a persistent HTTP connection. Railway's infrastructure handles this, but test under load. BullMQ job completion events must reliably reach the SSE controller. Polling fallback is acceptable for MVP.

- Cover letter PDF generation: puppeteer requires a headless Chrome instance — Railway supports this but test memory usage. @react-pdf/renderer is a lighter alternative that avoids a browser process entirely.

- Stripe webhook ordering: events don't always arrive in order. The webhook handler must be idempotent and handle out-of-order events gracefully (e.g., subscription.deleted arriving before subscription.updated).

- Prompt consistency: AI outputs are non-deterministic. The same CV + JD pair may return different scores on different calls. This is expected — but users who re-run an analysis and see a different score will be confused. Cache analysis results to ensure consistency.

## 11.4 Recommended Learning Priorities

| Topic | When | Why |
| --- | --- | --- |
| BullMQ + Redis | Day 1 | The queue is the spine of the AI pipeline. Understand job states, retry logic, and failed job handling before writing the analysis worker. |
| Stripe webhooks | Week 2 | Read the Stripe docs on webhook event handling cover-to-cover. Understand idempotency. Practice with the Stripe CLI event simulator. |
| OpenAI prompt engineering | Week 3 | Spend time on the OpenAI prompt engineering guide. Understand JSON mode, temperature, max_tokens, and prompt caching. Test manually before writing code. |
| Clerk Next.js integration | Week 1 | Read the Clerk Next.js quickstart. Understand ClerkProvider, useUser, auth(), and middleware. The auth layer touches every feature. |
| PostgreSQL RLS | Week 8 | Read the PostgreSQL row-level security documentation. Understand policies, roles, and how to test them. This is the database-layer security backstop. |

## 11.5 What to Build First

- Auth (Clerk) — Every other feature needs a user identity. No shortcuts.

- CV upload and parsing — The AI analysis is worthless without clean CV text.

- AI analysis — This is the product. Build and test this before billing.

- Billing — Build it as soon as the core loop works. Do not launch without it.

- Everything else — Polish after paying users exist.

## 11.6 What NOT to Build

- A CV builder. Users have CVs. The value is analysis, not creation.

- A job board. Adding job search turns CVPilot into a job platform — a completely different product.

- An AI chat interface. Direct OpenAI calls with structured prompts deliver the value. LangChain, RAG, and chat interfaces are complexity with no MVP benefit.

- Mobile apps. Web-responsive is sufficient. Native apps double your maintenance burden.

- Multi-language support. English-first. International expansion is a V3 problem.

- Team features. Validate single-user value before building collaboration.

- Anything that requires a sales call. The MVP should sell itself.

## 11.7 Common Mistakes That Delay Launch

| Mistake | Why It Delays Launch |
| --- | --- |
| Over-engineering the AI layer | Using LangChain, vector databases, or custom embeddings in the MVP. Direct OpenAI API calls are sufficient and far simpler. |
| Perfect before shipping | Spending weeks polishing a feature before real users have seen it. Ship at 80%, get feedback, iterate. |
| Building features in isolation | Building the full CV module before testing whether the AI produces useful output. Test the AI first — it's the riskiest assumption. |
| Skipping manual prompt testing | Writing the analysis worker before manually testing the prompt with real CVs. Every hour of manual testing saves five hours of debugging. |
| Ignoring Stripe webhook idempotency | Processing the same Stripe event twice. This causes double-charging bugs. Test duplicate events explicitly in week 6. |
| Not time-boxing sprints | Letting a sprint run 2 weeks instead of 1 because one feature is 'almost done'. Carry it over. Keep the cadence. |
| Building a custom auth system | Any time spent on JWT, sessions, or password hashing is time not spent on the product. Clerk solves this correctly. |
| Delaying security to 'later' | Later never comes before launch. Security hardening is in Sprint 7 — it is non-negotiable and has a fixed week in the calendar. |

## 11.8 The One Rule

Ship something a student can pay for in 10 weeks. Then talk to 20 of them. Every subsequent decision follows from what they tell you. The roadmap is not a commitment — it is a hypothesis. The users will rewrite it for you.

## Document Control

| Document Title | CVPilot — Implementation Roadmap |
| --- | --- |
| Version | 1.0 |
| Status | Approved for Execution |
| Date | June 2025 |
| References | PRD v1.0 · Architecture Document v1.0 |

This document is confidential. It is an execution guide for the founding engineering team. Decisions made during implementation that deviate from this roadmap should be documented as Architecture Decision Records (ADRs) in the /docs folder.